## Migration Tasks
ID | Slim Objects | Dev & Testing | Dev & Testing Start Date | Dev & Testing End Date | Dev & Testing Status | Historical Data | Historical Data Start Date | Historical Data End Date | Historical Data Status | Dependencies
1 | Import Control | 47 | 2026-05-17 | 2026-07-27 | In-Progress
2 | Article Filter | 2 | 2026-05-20 | 2026-05-21 | Finished |  |  |  |  | 1
3 | Transactions | 3 | 2026-05-31 | 2026-06-02 | On-Hold | 7 | 2026-06-03 | 2026-06-11 | Finished | 2
3 | Vacation | 0 | 2026-05-24 | 2026-05-28 | Not-Started |  |  |  |  | 2
4 | Article Code Master | 3 | 2026-06-14 | 2026-06-16 | Finished |  |  |  |  | 3
5 | Stock Details | 3 | 2026-06-17 | 2026-06-21 | In-Progress |  |  |  |  | 4
6 | Purchase Order | 4 | 2026-06-22 | 2026-06-25 | In-Progress |  |  |  |  | 5
7 | Suppliers | 3 | 2026-06-28 | 2026-06-30 | Not-Started |  |  |  |  | 6
8 | Warehouse Master | 2 | 2026-07-01 | 2026-07-02 | Not-Started |  |  |  |  | 7
9 | Bill Of Material | 4 | 2026-07-05 | 2026-07-08 | Not-Started |  |  |  |  | 8
10 | Historical PO | 3 | 2026-07-09 | 2026-07-13 | Not-Started | 10 | 2026-07-14 | 2026-07-27 | Not-Started | 9
11 | UAT - General Testing | 5 | 2026-07-28 | 2026-08-03 | Not-Started |  |  |  |  | 10
12 | Develope ETL for Testing Envir. | 3 | 2026-08-04 | 2026-08-06 | Not-Started |  |  |  |  | 11